## full roads spreadsheet
Approved Ogden Township Road Projects 2022
PROJECT | Estimate | Down pmt. | Payment | Payment | Payment | Paid to date | Total Match Used: | Variance | Match Funds
EST # 4336- .96 Miles of Fike Rd, Crockett to Neuroth | 38790.52 | 19395.26 |  |  |  | 19395.26 | 16044.4 | 3350.86 | 2294.76 | Invoice #102291
|  | Deposit | [6 empty] | 13749.64 | Invoice #102377
Check #6688
EST #4384- 2.00 Miles of Pence Hwy, Weston to Mulberry Rd | 49488.56 | 24744.28 | 2268.82 | 181.56 |  | 27194.66 | 22196.94 | 96.96 | 3400 | Invoice #102292
|  | Desposit | Invoice #102463 | Invoice # 102554 |  |  |  |  | 18796.94 | Invoice #102379
|  | Check #6687 | Check #6819 | Check#6818
EST#4514- .99 Miles of Thompson Hwy, Yankee to Mulberry ( JOINT W/RIGA) | 72754.09 | 36377.04 | 33004.06 | 71.96 |  | 69453.06 |  | 3301.03
|  | Deposit | Invoice #102576 | Invoice #102591
|  | Check #6689 | Check #6858 | Check #6857
EST#4515- 99 Miles of Treat Hwy, Horton to Fike (JOINT PROJECT W/FAIRFIELD) | 88336.25 | 44168.12 | 37917.8 | 420.58 |  | 82506.5 |  | 5829.75
|  | Deposit | Invoice #102574 | Invoice #102590
|  | Check #6690 | Check #6855 | Check #6856
EST# 4533-87" x 63" x 48' Culvert Replacement on Fike rd, Crockett to Loar- Bay Drain | 13269.47 | 6634.74 | 2062.63 | 4515.51 |  | 13212.88 |  | 56.59
|  | Deposit | Invoice#102378 | Invoice #102553
|  | Check # | Check#6816 | Check#6817
EST# 4551- 1.99 Miles of Ridgeville- Crockett to Pence | 151330.85 | 73026.79 | 15968.92 | 3623.69 |  | 92619.4 | 37108.43 | 21603.02 | 37108.43 | Invoice #102380
-146053.59 |  | Deposit | Invoice#102380 | Invoice #102464
|  | Check #6705 | Check #6860 | Check #6861
EST#4552- 1.71 Miles of Neuroth Hwy- Ohio line to Mulberry Rd | 8249.92 | 4124.96 | 2795.22 |  |  | 6920.18 |  | 1329.74
|  | Deposit | Invoice#102293
|  | Check #6706 | Check #6859
Total Road Bids | 422219.66 |  |  |  |  | Total PAID | Total Match | Variance
Paid to date | [5 empty] | 311301.94 | 75349.77 | 35567.95

## Sheet1
Approved Ogden Township Road Projects 2020
PROJECT | Estimate | Down pmt. | Payment | Payment | Payment | Payment | Paid to date | Variance
# 4066- Hendricks Road Between Loar & Crockett | 44956.11 | 15734.64 |  |  |  |  | 15734.64
# 3373- Loar Hwy- Yankee to Ohio line | 30182.29 | 10566.24 |  |  |  |  | 10566.24
#3374-Yankee Road- Pence to Hodges | 22022.86 | 7708 |  |  |  |  | 7708
#3866-Loar Hwy- Horton to Fike | 23422.56 | 10476.34 |  |  |  |  | 10476.34
#4017-Yankee Rd-Pence to Crockett | 43532.85 | 18057.43 |  |  |  |  | 18057.43
#4068-Culverts on Thompson Hwy | 4933.13 | 1726.6 |  |  |  |  | 1726.6
#4069- Neuroth- Weston to Fike | 29442.27 | 10304.79 |  |  |  |  | 10304.79
#4125- Fike Road-Thompson to Loar Hwy | 25321.27 | 8862.44 |  |  |  |  | 8862.44
#4127- Loar Hwy- Mulberry to Weston | 37612.72 | 13164.45 |  |  |  |  | 13164.45
#3604- Pence Hwy- Yankee to Ohio Line | 26161.52 | 9156.53 |  |  |  |  | 9156.53
0
0
0
0
0
0
0
0
0
0
Total Road Bids | 287587.58
Paid to date | [6 empty] | 105757.46
Variance from estimates | TOTAL

## 2022 Approved&denied
Proposed Ogden Township Road Projects 2022
Estimate # | Description | Estimated Total Cost | Downpayment Required | Accepted or Rejected | Reason ( if rejected )
4336 | Asphalt wedge, crackfill, seal coat & fog seal .96 Miles of Fike Rd, Crockett to Neuroth | 38790.52 | 19395.26 | APPROVED
4384 | Crackfill, Seal coat & fog seal 2.00 Miles of Pence Hwy, Weston to Mulberry Rd | 49488.56 | 24744.28 | APPROVED
4385 | Shoulder Removal, 18", Culv & Ashpalt Overlay 1.16 Miles of Sheldon Rd, Crockett to Scott Hwy | 0 | 0 | REJECTED | Rejected at this time in order to obtain other options for Sheldon Road. Pending other options from LCRC for May 2022 Meeting
4514 | Shoulder Removal, Underseal & Aspalt overlay .99 Miles of Thompson Hwy, Yankee to Mulberry ( JOINT PROJECT WITH RIGA) | 72754.09 | 36377.04 | APPROVED
4515 | Underseal & Aspalt overlay .99 Miles of Treat Hwy, Horton to Fike (JOINT PROJECT WITH FAIRFIELD) | 88336.25 | 44168.12 | APPROVED
4533 | 87" x 63" x 48' Culvert Replacement on Fike rd, Crockett to Loar- Bay Drain | 13269.47 | 6634.74 | APPROVED
TOTALS: |  | 262638.89 | 131319.44